## TUNISIA (TN)
Summary
-Add filters to Row 8, -Select FA Type, and Brand -Summary table will update in Row 6
FA Type | [5 empty] | #Car Park | Completed |  |  | Achiev. Rate | Target expect. | C. Rate vs. Target | Delta to Target | Total Green | Total Red
Total | [5 empty] | 456 | 23 |  |  | 5.044% | 176.7097 | 13.02% | -153.7097 | 4 | 19
FA Type | Region | Country | FA Code | Desc | Brand | #Car Park | Completed | Remedy Instructions (Dealer Inst.) Released Via TechConnect | weeks | Achiev. Rate | Target expect. | C. Rate vs. Target | Green | Takata | Company | NTW | KPI Curve Status | Delta to Target
CSN | MEA | TUNISIA (TN) | 05A | Jeep Compass / Renegade - 222016EE-OIL LEAKAGE FROM DDCT TRANSMISSION LOWER COVER | CJDR | 38 | 2 | 2023-02-04 | 16 | 5.263% | 16.15 | 12.38% | 42.5% |  | Ex-F | CJDR | R | -14.15 | 0 | 1
SR | MEA | TUNISIA (TN) | 28A | 2020-2022 JL FRAME STUD | CJDR | 2 | 1 | 2023-04-28 | 4 | 50% | 0 | 0% | 0% |  | Ex-F | CJDR | R | 1 | 0 | 1
SR | MEA | TUNISIA (TN) | W58 | 2014-2018 WK & DS LOSS OF CRANKSHAFT POSITION | CJDR | 1 | 1 | 2022-05-09 | 55 | 100% | 0.5177 | 193.2% | 51.77% |  | Ex-F | CJDR | G | 0.4823 | 1 | 0
SR | MEA | TUNISIA (TN) | Y93 | 2021 - 2022 Compass DRL R1 Low software | CJDR | 2 | 2 | 2022-02-28 | 65 | 100% | 1.7 | 117.6% | 85% |  | Ex-F | CJDR | G | 0.3 | 1 | 0
CSN | MEA | TUNISIA (TN) | YA8 | 2022 MP R1 Radio with Android Auto & Car Play Certification | CJDR | 1 | 1 | 2022-02-08 | 68 | 100% | 0.786 | 127.2% | 78.6% |  | Ex-F | CJDR | G | 0.214 | 1 | 0
CSN | MEA | TUNISIA (TN) | Z39 | 2021 - 2022 BV AC Compressor Ground Bolt | CJDR | 5 | 0 | 2022-05-23 | 53 | 0% | 3.76 | 0% | 75.2% |  | Ex-F | CJDR | R | -3.76 | 0 | 1
CSN | MEA | TUNISIA (TN) | ZD8 | 21-22MY JL GMET-4 Water Pump Coolant Leak | CJDR | 5 | 0 | 2022-12-09 | 24 | 0% | 2.735 | 0% | 54.7% |  | Ex-F | CJDR | R | -2.735 | 0 | 1
RSU | MEA | TUNISIA (TN) | Y77 | 2021-2022 MV Shift Lever (Automatic) | CJDR | 1 | 1 | 2021-11-29 | 78 | 100% | 0.7 | 142.9% | 70% |  | Ex-F | CJDR | G | 0.3 | 1 | 0
RSU | MEA | TUNISIA (TN) | KLR | Landtrek Projecteur | AP | 224 | 163 | 2021-06-18 | 101 | 72.77% | 156.8 | 104% | 70% |  | Ex-P | PCDOV | G | 6.2 | 1 | 0
CSN | MEA | TUNISIA (TN) | KNR | 208(P21), 2008(P24) Convertisseur | AP | 6 | 6 | 2021-06-29 | 100 | 100% | 4.8 | 125% | 80% |  | Ex-P | PCDOV | G | 1.2 | 1 | 0
SR | MEA | TUNISIA (TN) | KPJ | Landtrek Faisceau airbag | AP | 345 | 309 | 2021-07-26 | 96 | 89.57% | 307.3163 | 100.5% | 89.08% |  | Ex-P | PCDOV | G | 1.6837 | 1 | 0
CSN | MEA | TUNISIA (TN) | KMT | 208 (P21) : Amortisseurs | AP | 4 | 4 | 2021-07-26 | 96 | 100% | 3.2 | 125% | 80% |  | Ex-P | PCDOV | G | 0.8 | 1 | 0
CSN | MEA | TUNISIA (TN) | KMU | 208(P21) : Lève vitre | AP | 2 | 2 | 2021-07-26 | 96 | 100% | 1.6 | 125% | 80% |  | Ex-P | PCDOV | G | 0.4 | 1 | 0
RSU | MEA | TUNISIA (TN) | KPG | Traveller, Expert 4, 3008(P84), 5008(P87) : Emetteur embrayage | AP | 10 | 10 | 2021-07-26 | 96 | 100% | 7 | 142.9% | 70% |  | Ex-P | PCDOV | G | 3 | 1 | 0
RSU | MEA | TUNISIA (TN) | HUG | Spacetourer, Jumpy IV, C5 Aircross : Emetteur embrayage | AC | 1 | 1 | 2021-07-27 | 96 | 100% | 0.7 | 142.9% | 70% |  | Ex-P | PCDOV | G | 0.3 | 1 | 0
RSU | MEA | TUNISIA (TN) | HRD | DS7 Crossback Feux arrière | DS | 3 | 2 | 2021-08-06 | 94 | 66.67% | 2.1 | 95.24% | 70% |  | Ex-P | PCDOV | R | -0.1 | 0 | 1
CSN | MEA | TUNISIA (TN) | KPT | TRAVELLER, EXPERT 4 Faisceau électrique | AP | 10 | 9 | 2021-09-03 | 90 | 90% | 8 | 112.5% | 80% |  | Ex-P | PCDOV | G | 1 | 1 | 0
CSN | MEA | TUNISIA (TN) | KPU | Traveller, Expert 4, 3008(P84), 5008(P87) : Emetteur embrayage | AP | 47 | 43 | 2021-09-13 | 89 | 91.49% | 37.6 | 114.4% | 80% |  | Ex-P | PCDOV | G | 5.4 | 1 | 0
CSN | MEA | TUNISIA (TN) | KJM | Pick up Moteur | AP | 579 | 400 | 2021-10-12 | 85 | 69.08% | 462.9105 | 86.41% | 79.95% |  | Ex-P | PCDOV | R | -62.9105 | 0 | 1
RSU | MEA | TUNISIA (TN) | KQZ | Traveller, Expert 4 Fixation balai essuie-vitre | AP | 9 | 9 | 2021-10-25 | 83 | 100% | 6.3 | 142.9% | 70% |  | Ex-P | PCDOV | G | 2.7 | 1 | 0
RSU | MEA | TUNISIA (TN) | HWG | Spacetourer, Jumpy IV Fixation balai essuie-vitre | AC | 2 | 2 | 2021-10-26 | 83 | 100% | 1.4 | 142.9% | 70% |  | Ex-P | PCDOV | G | 0.6 | 1 | 0
RSU | MEA | TUNISIA (TN) | O4K | Combo E - Turbo Charger Oil Feed Pipe | OV | 1 | 1 | 2021-11-17 | 80 | 100% | 0.7 | 142.9% | 70% |  | Ex-P | PCDOV | G | 0.3 | 1 | 0
SR | MEA | TUNISIA (TN) | KQR | 301 Transmission droite | AP | 31 | 20 | 2021-11-29 | 78 | 64.52% | 26.97 | 74.16% | 87% |  | Ex-P | PCDOV | R | -6.97 | 0 | 1
RSU | MEA | TUNISIA (TN) | O4G | Astra K - Air Deflector | OV | 7 | 7 | 2021-12-01 | 78 | 100% | 4.9 | 142.9% | 70% |  | Ex-P | PCDOV | G | 2.1 | 1 | 0
RSU | MEA | TUNISIA (TN) | O2Z | CSS Engine - Software Update | OV | 1 | 1 | 2022-01-07 | 72 | 100% | 0.699 | 143.1% | 69.9% |  | Ex-P | PCDOV | G | 0.301 | 1 | 0
RSU | MEA | TUNISIA (TN) | KUN | 208(P21), 2008(P24) Platine contacteur | AP | 3 | 3 | 2022-01-21 | 70 | 100% | 2.091 | 143.5% | 69.7% |  | Ex-P | PCDOV | G | 0.909 | 1 | 0
SR | MEA | TUNISIA (TN) | KTA | 308(T9), 3008(P84), 5008(P87), 508(R8), Traveller, Expert 4 Logiciel moteur | AP | 27 | 27 | 2022-01-28 | 69 | 100% | 23.1161 | 116.8% | 85.62% |  | Ex-P | PCDOV | G | 3.8839 | 1 | 0
SR | MEA | TUNISIA (TN) | O6B | Corsa F Indicateur de direction | OV | 2 | 2 | 2022-02-22 | 66 | 100% | 1.7031 | 117.4% | 85.15% |  | Ex-P | PCDOV | G | 0.29692 | 1 | 0
RSU | MEA | TUNISIA (TN) | KVK | Boxer Emetteur embrayage | AP | 36 | 35 | 2022-03-31 | 61 | 97.22% | 24.552 | 142.6% | 68.2% |  | Ex-P | PCDOV | G | 10.448 | 1 | 0
RSU | MEA | TUNISIA (TN) | KVP | Boxer Boite à gants | AP | 23 | 22 | 2022-03-28 | 61 | 95.65% | 15.686 | 140.3% | 68.2% |  | Ex-P | PCDOV | G | 6.314 | 1 | 0
CSN | MEA | TUNISIA (TN) | KWC | 3008(P84), 5008(P87), Rifter, Partner(K9), Traveller, Expert 4 Compresseur | AP | 5 | 5 | 2022-04-26 | 57 | 100% | 3.82 | 130.9% | 76.4% |  | Ex-P | PCDOV | G | 1.18 | 1 | 0
CSN | MEA | TUNISIA (TN) | KYA | 3008(P84), 5008(P87) Enjoliveur pare-brise | AP | 13 | 10 | 2022-05-13 | 54 | 76.92% | 9.815 | 101.9% | 75.5% |  | Ex-P | PCDOV | G | 0.185 | 1 | 0
SR | MEA | TUNISIA (TN) | KVR | (308(T9), 3008(P84), 5008(P87), 508(R8), Traveller, Expert 4 Logiciel moteur) | AP | 129 | 80 | 2022-06-09 | 51 | 62.02% | 105.135 | 76.09% | 81.5% |  | Ex-P | PCDOV | R | -25.135 | 0 | 1
SR | MEA | TUNISIA (TN) | JBG | (C4 Spacetourer(B78), C5 Aircross, DS7 Crossback, Spacetourer, Jumpy IV Logiciel moteur) | AC | 1 | 1 | 2022-06-09 | 51 | 100% | 0.815 | 122.7% | 81.5% |  | Ex-P | PCDOV | G | 0.185 | 1 | 0
SR | MEA | TUNISIA (TN) | KVL | KVL 208(P21) Tuyau carburant | AP | 311 | 96 | 2022-07-28 | 44 | 30.87% | 241.958 | 39.68% | 77.8% |  | Ex-P | PCDOV | R | -145.958 | 0 | 1
CSN | MEA | TUNISIA (TN) | KAV | Cross Carline - Multifunction Control Un | OV | 18 | 18 | 2022-08-02 | 43 | 100% | 12.816 | 140.4% | 71.2% |  | Ex-P | PCDOV | G | 5.184 | 1 | 0
RSU | MEA | TUNISIA (TN) | KBH | LXD Engine - Oil Pressure Management | OV | 1 | 1 | 2022-08-01 | 43 | 100% | 0.591 | 169.2% | 59.1% |  | Ex-P | PCDOV | G | 0.409 | 1 | 0
CSN | MEA | TUNISIA (TN) | MB4 | 208(P21) Tuyau d'eau | AP | 3 | 3 | 2022-09-22 | 36 | 100% | 2.001 | 149.9% | 66.7% |  | Ex-P | PCDOV | G | 0.999 | 1 | 0
RSU | MEA | TUNISIA (TN) | MAM | 2008, 3008, 5008, 508 Télécommande | AP | 7 | 6 | 2022-09-21 | 36 | 85.71% | 3.773 | 159% | 53.9% |  | Ex-P | PCDOV | G | 2.227 | 1 | 0
RSU | MEA | TUNISIA (TN) | MCA | Traveller, Expert 4 Fixation tuyau de carburant | AP | 7 | 6 | 2022-09-28 | 35 | 85.71% | 3.703 | 162% | 52.9% |  | Ex-P | PCDOV | G | 2.297 | 1 | 0
SR | MEA | TUNISIA (TN) | KBT | Insignia B - Brake Performance | OV | 4 | 3 | 2022-10-10 | 33 | 75% | 1.6408 | 182.8% | 41.02% |  | Ex-P | PCDOV | G | 1.3592 | 1 | 0
RSU | MEA | TUNISIA (TN) | MCJ | 208(P21), 301, RIFTER, PARTNER(K9) Fixation pompe à eau | AP | 31 | 30 | 2022-10-14 | 32 | 96.77% | 15.469 | 193.9% | 49.9% |  | Ex-P | PCDOV | G | 14.531 | 1 | 0
CSN | MEA | TUNISIA (TN) | MCT | 208(P21), 2008(P24) Direction assistée | AP | 1 | 0 | 2022-11-15 | 28 | 0% | 0.593 | 0% | 59.3% |  | Ex-P | PCDOV | R | -0.593 | 0 | 1
SR | MEA | TUNISIA (TN) | KUZ | Rifter, Partner(K9) Protection sous moteur | AP | 2109 | 664 | 2022-11-29 | 26 | 31.48% | 1363.8481 | 48.69% | 64.67% |  | Ex-P | PCDOV | R | -699.8481 | 0 | 1
SR | MEA | TUNISIA (TN) | JAP | Berlingo(K9) Protection sous moteur | AC | 774 | 44 | 2022-11-29 | 26 | 5.685% | 500.5303 | 8.791% | 64.67% |  | Ex-P | PCDOV | R | -456.5303 | 0 | 1
CSN | MEA | TUNISIA (TN) | MDJ | 208(P21), 2008(P24) Logiciel DAE | AP | 17 | 15 | 2022-11-29 | 26 | 88.24% | 9.707 | 154.5% | 57.1% |  | Ex-P | PCDOV | G | 5.293 | 1 | 0
RSU | MEA | TUNISIA (TN) | KDM | Camera 360° software | OV | 1 | 1 | 2022-11-28 | 26 | 100% | 0.433 | 230.9% | 43.3% |  | Ex-P | PCDOV | G | 0.567 | 1 | 0
RSU | MEA | TUNISIA (TN) | KD5 | Exterior Camera Connection | OV | 1 | 1 | 2022-11-28 | 26 | 100% | 0.433 | 230.9% | 43.3% |  | Ex-P | PCDOV | G | 0.567 | 1 | 0
SR | MEA | TUNISIA (TN) | KGH | Tous types Courroie distribution | AP | 1079 | 229 | 2022-12-08 | 25 | 21.22% | 366.5363 | 62.48% | 33.97% |  | Ex-P | PCDOV | R | -137.5363 | 0 | 1
SR | MEA | TUNISIA (TN) | KGG | Tous types Courroie distribution | AP | 19 | 3 | 2022-12-08 | 25 | 15.79% | 6.4543 | 46.48% | 33.97% |  | Ex-P | PCDOV | R | -3.4543 | 0 | 1
RSU | MEA | TUNISIA (TN) | O5U | Mokka (P2QO) - Glovebox | OV | 2 | 2 | 2022-12-06 | 25 | 100% | 0.842 | 237.5% | 42.1% |  | Ex-P | PCDOV | G | 1.158 | 1 | 0
SR | MEA | TUNISIA (TN) | HLX | Tous types Courroie distribution | AC | 375 | 34 | 2022-12-09 | 24 | 9.067% | 123.2625 | 27.58% | 32.87% |  | Ex-P | PCDOV | R | -89.2625 | 0 | 1
RSU | MEA | TUNISIA (TN) | KDL | Mokka - Collage joint d'étanchéité capot moteur | OV | 79 | 26 | 2022-12-12 | 24 | 32.91% | 32.311 | 80.47% | 40.9% |  | Ex-P | PCDOV | R | -6.311 | 0 | 1
RSU | MEA | TUNISIA (TN) | MDR | Tous types DV6 Serrage BSE | AP | 59 | 45 | 2022-12-15 | 24 | 76.27% | 24.131 | 186.5% | 40.9% |  | Ex-P | PCDOV | G | 20.869 | 1 | 0
RSU | MEA | TUNISIA (TN) | JNW | Tous types DV6 Serrage BSE | AC | 7 | 7 | 2022-12-15 | 24 | 100% | 2.863 | 244.5% | 40.9% |  | Ex-P | PCDOV | G | 4.137 | 1 | 0
RSU | MEA | TUNISIA (TN) | JPF | Spacetourer, Jumpy IV Point de soudure | AC | 4 | 0 | 2022-12-14 | 24 | 0% | 1.636 | 0% | 40.9% |  | Ex-P | PCDOV | R | -1.636 | 0 | 1
RSU | MEA | TUNISIA (TN) | KEC | Water Outlet Box | OV | 4 | 3 | 2022-12-15 | 24 | 75% | 1.636 | 183.4% | 40.9% |  | Ex-P | PCDOV | G | 1.364 | 1 | 0
RSU | MEA | TUNISIA (TN) | KDN | Mokka - Pose joint d'étanchéité capot moteur | OV | 3 | 0 | 2022-12-09 | 24 | 0% | 1.227 | 0% | 40.9% |  | Ex-P | PCDOV | R | -1.227 | 0 | 1
RSU | MEA | TUNISIA (TN) | MD1 | Traveller, Expert 4 Point de soudure | AP | 2 | 2 | 2022-12-14 | 24 | 100% | 0.818 | 244.5% | 40.9% |  | Ex-P | PCDOV | G | 1.182 | 1 | 0
SR | MEA | TUNISIA (TN) | MDX | 208(P21) Frein à main | AP | 435 | 147 | 2022-12-19 | 23 | 33.79% | 266.0765 | 55.25% | 61.17% |  | Ex-P | PCDOV | R | -119.0765 | 0 | 1
RSU | MEA | TUNISIA (TN) | MBL | 308(P5) Logiciels | AP | 9 | 6 | 2022-12-19 | 23 | 66.67% | 3.573 | 167.9% | 39.7% |  | Ex-P | PCDOV | G | 2.427 | 1 | 0
RSU | MEA | TUNISIA (TN) | JNR | Berlingo (K9) Equilibreur volet | AC | 1 | 0 | 2022-12-19 | 23 | 0% | 0.397 | 0% | 39.7% |  | Ex-P | PCDOV | R | -0.397 | 0 | 1
RSU | MEA | TUNISIA (TN) | MDK | Rifter, Partner(K9) Equilibreur volet | AP | 1 | 1 | 2022-12-19 | 23 | 100% | 0.397 | 251.9% | 39.7% |  | Ex-P | PCDOV | G | 0.603 | 1 | 0
SR | MEA | TUNISIA (TN) | MDZ | 208(P21) Biellette de direction | AP | 284 | 48 | 2022-12-26 | 22 | 16.9% | 170.4 | 28.17% | 60% |  | Ex-P | PCDOV | R | -122.4 | 0 | 1
CSN | MEA | TUNISIA (TN) | JAQ | DS7 Crossback Feux arrière | DS | 91 | 4 | 2023-01-05 | 21 | 4.396% | 26.9087 | 14.87% | 29.57% |  | Ex-P | PCDOV | R | -22.9087 | 0 | 1
RSU | MEA | TUNISIA (TN) | MEC | Landtrek Liquide de refroidissement | AP | 1956 | 1025 | 2023-01-17 | 19 | 52.4% | 665.04 | 154.1% | 34% |  | Ex-P | PCDOV | G | 359.96 | 1 | 0
RSU | MEA | TUNISIA (TN) | MDS | 3008(P84), 5008(P87) Vitre porte avant | AP | 4 | 3 | 2023-01-24 | 18 | 75% | 1.3 | 230.8% | 32.5% |  | Ex-P | PCDOV | G | 1.7 | 1 | 0
RSU | MEA | TUNISIA (TN) | KEJ | Mokka (P2QO) - Joint de porte AR gauche | OV | 1 | 0 | 2023-01-27 | 17 | 0% | 0.31 | 0% | 31% |  | Ex-P | PCDOV | R | -0.31 | 0 | 1
CSN | MEA | TUNISIA (TN) | MD5 | Rifter, Partner(K9) Equilibreur de volet | AP | 28 | 17 | 2023-02-09 | 16 | 60.71% | 11.9 | 142.9% | 42.5% |  | Ex-P | PCDOV | G | 5.1 | 1 | 0
SR | MEA | TUNISIA (TN) | MEQ | 308(P5), 408, 508(R8) Serrage | AP | 1 | 1 | 2023-02-07 | 16 | 100% | 0.4928 | 202.9% | 49.28% |  | Ex-P | PCDOV | G | 0.5072 | 1 | 0
SR | MEA | TUNISIA (TN) | MEA | 301 Logiciel BSI | AP | 3 | 2 | 2023-02-21 | 14 | 66.67% | 1.3392 | 149.3% | 44.64% |  | Ex-P | PCDOV | G | 0.6608 | 1 | 0
CSN | MEA | TUNISIA (TN) | MFE | Traveller, Expert 4 Information roue | AP | 10 | 10 | 2023-03-28 | 9 | 100% | 2.55 | 392.2% | 25.5% |  | Ex-P | PCDOV | G | 7.45 | 1 | 0
RSU | MEA | TUNISIA (TN) | MDU | Tous types Pompe à eau | AP | 23 | 2 | 2023-03-28 | 9 | 8.696% | 3.565 | 56.1% | 15.5% |  | Ex-P | PCDOV | R | -1.565 | 0 | 1
RSU | MEA | TUNISIA (TN) | JNZ | Tous types Pompe à eau | DS | 1 | 0 | 2023-03-28 | 9 | 0% | 0.155 | 0% | 15.5% |  | Ex-P | PCDOV | R | -0.155 | 0 | 1
CSN | MEA | TUNISIA (TN) | MC6 | 5008(P87), Traveller, Expert 4, Boxer Boitier sortie d'eau | AP | 30 | 8 | 2023-05-05 | 3 | 26.67% | 3e-05 | 26666667% | 0.0001% |  | Ex-P | PCDOV | G | 8 | 1 | 0
CSN | MEA | TUNISIA (TN) | JMR | Spacetourer, Jumpy IV, Jumper Boitier sortie d'eau | AC | 2 | 0 | 2023-05-08 | 3 | 0% | 2e-06 | 0% | 0.0001% |  | Ex-P | PCDOV | R | -2e-06 | 0 | 1
RSU | MEA | TUNISIA (TN) | MGG | Traveller, Expert 4 Joint d'étanchéité | AP | 36 | 2 | 2023-05-10 | 3 | 5.556% | 3.6e-05 | 5555556% | 0.0001% |  | Ex-P | PCDOV | G | 2 | 1 | 0
RSU | MEA | TUNISIA (TN) | JTR | Spacetourer, Jumpy IV Joint d'étanchéité | AC | 9 | 1 | 2023-05-10 | 3 | 11.11% | 9e-06 | 11111111% | 0.0001% |  | Ex-P | PCDOV | G | 0.99999 | 1 | 0
RSU | MEA | TUNISIA (TN) | MGD | EP6 TTypes : Capteur cliquetis | AP | 28 | 0 | 2023-05-12 | 2 | 0% | 2.8e-05 | 0% | 0.0001% |  | Ex-P | PCDOV | R | -2.8e-05 | 0 | 1
RSU | MEA | TUNISIA (TN) | 6611 | 356-357-ECU | FIAT | 107 | 0 | 2023-04-04 | 8 | 0% | 13.91 | 0% | 13% |  | Ex-F | FLAPH | R | -13.91 | 0 | 1
CSN | MEA | TUNISIA (TN) | 6605 | 150-312-Serb.ol | FIAT | 24 | 0 | 2023-04-03 | 8 | 0% | 5.28 | 0% | 22% |  | Ex-F | FLAPH | R | -5.28 | 0 | 1
RSU | MEA | TUNISIA (TN) | 6538 | Termostato | FIAT | 21 | 2 | 2022-12-02 | 25 | 9.524% | 8.841 | 22.62% | 42.1% |  | Ex-F | FLAPH | R | -6.841 | 0 | 1
RSU | MEA | TUNISIA (TN) | 6540 | 334-CRISTALLO | FIAT | 24 | 2 | 2022-12-07 | 25 | 8.333% | 10.104 | 19.79% | 42.1% |  | Ex-F | FLAPH | R | -8.104 | 0 | 1
RSU | MEA | TUNISIA (TN) | 6541 | Termostato | FIAT Pro | 3 | 0 | 2022-12-02 | 25 | 0% | 1.263 | 0% | 42.1% |  | Ex-F | FLAPH | R | -1.263 | 0 | 1
RSU | MEA | TUNISIA (TN) | 6526 | 356-357-Blow-by | Fiat Pro | 155 | 0 | 2022-11-21 | 27 | 0% | 68.975 | 0% | 44.5% |  | Ex-F | FLAPH | R | -68.975 | 0 | 1
RSU | MEA | TUNISIA (TN) | 6517 | 356-Tappeto | FIAT | 4 | 0 | 2022-10-10 | 33 | 0% | 2.036 | 0% | 50.9% |  | Ex-F | FLAPH | R | -2.036 | 0 | 1
RSU | MEA | TUNISIA (TN) | 6512 | 290-295-505-Fre | Fiat Pro | 3 | 0 | 2022-09-23 | 35 | 0% | 1.587 | 0% | 52.9% |  | Ex-F | FLAPH | R | -1.587 | 0 | 1
RSU | MEA | TUNISIA (TN) | 6431 | 290-295-505-CAS | Fiat pro | 6 | 0 | 2022-03-07 | 64 | 0% | 4.128 | 0% | 68.8% |  | Ex-F | FLAPH | R | -4.128 | 0 | 1
RSU | MEA | TUNISIA (TN) | 6425 | 290-295-CIL MAE | Fiat Pro | 10 | 0 | 2022-02-25 | 65 | 0% | 6.9 | 0% | 69% |  | Ex-F | FLAPH | R | -6.9 | 0 | 1
RSU | MEA | TUNISIA (TN) | 6416 | 150-Semiassi | FIAT | 14 | 3 | 2022-02-16 | 67 | 21.43% | 9.716 | 30.88% | 69.4% |  | Ex-F | FLAPH | R | -6.716 | 0 | 1
RSU | MEA | TUNISIA (TN) | 6418 | 150-GUARNIZIONI | FIAT | 5 | 0 | 2022-02-09 | 68 | 0% | 3.475 | 0% | 69.5% |  | Ex-F | FLAPH | R | -3.475 | 0 | 1
RSU | MEA | TUNISIA (TN) | 6340 | C635/C637 | Fiat Pro | 18 | 8 | 2021-06-24 | 101 | 44.44% | 12.6 | 63.49% | 70% |  | Ex-F | FLAPH | R | -4.6 | 0 | 1
RSU | MEA | TUNISIA (TN) | 22-012 | 21MY MV 1.3 GSE S&S ENGINE STOP | CJDR | 2 |  | 2022-01-19 | 71 | 0% | 1.396 | 0% | 69.8% |  | Ex-F | CJDR | R | -1.396 | 0 | 1
RSU | MEA | TUNISIA (TN) | 23-120 | 22-23MY JL WATER LEAK - LIFTGATE GLASS TO SWING GA | CJDR | 5 |  | 2023-05-02 | 4 | 0% | 0.15 | 0% | 3% |  | Ex-F | CJDR | R | -0.15 | 0 | 1